## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Look into scheduling managment solutions | 1 | 1 | 1
2 | Get up to date on codebase |  |  | 1
3 | Connect with sponsor on access |  |  | 1
4 | Run program locally |  |  | 1
5 | Send meeting reminder emails |  |  | 1
6 | Connecting with sponsor and getting into the website/code | 2 | 1 | 1
7 | Update database with unique mentor's booking links |  |  | 2
8 | Attendance tracking fixes |  |  | 2
9 | Fix web certificate |  |  | 2
10 | Attendance tracking implementation |  |  | 2
11 | Excel batch new student add/ mentorship assignment |  |  | 2
12
13
14
17 | User Guide for Professors to Update Scheduling Features |  |  | 3
18 | Continous cyber improvements |  |  | 3
19 | Documentation for Azure, Bookings, Cybersecurity |  |  | 3
| Test cases |  |  | 3
New Browser Page: Professor View of Student Log​
Student Meeting Log Drop-Down to Check Boxes
20
21